## Sheet1
ATEK BANK
Scrum – sprint -1(project Baseline)
Database wireframe preparation	04-05-2019
Database Script preparation	06-05-2019
Database Review/execution	07-05-2019
Abstraction Document Preparation	07-05-2019
Project – Baseline setup	07-05-2019
Project – maven integration with dependencies	07-05-2019
Project – Identify the business objects	07-05-2019
Project – display menu items	07-05-2019
Adding – Common Modules (Login module, Payment module, Utilities)	08-05-2019
Project – Validation Implementation (UI Layer)	08-05-2019
Project – DAO Implementation (DAO Layer)	08-05-2019
Servlet/Controller Implementation	09-05-2019
Service/Business Implementation	09-05-2019
Feature wise – DAO Implementation	10-05-2019
Utilities – Common Functionality Implementation	10-05-2019
JavaScript Session part 1	14-05-2019
Project Updates, Agile Introduction	14-05-2019
Project Demo	14-05-2019
one to one Discussions	14-05-2019
SQL Batch Update- Sample	15-05-2019
Junit Session	15-05-2019
Log4j session	15-05-2019
Utilities – External Utility API (String Utils, File Utils)	16-05-2019
Convert Dynamic web -> Maven Project	16-05-2019
JavaScript (Page redirect, Dialog boxes, HTML DOM, Validations) (Part-2)	17-05-2019
One to one Questions	17-05-2019
Project Demo – 2nd Review	17-05-2019
Assessment- L2 & L3	17-05-2019
Scenario based Questions (discussion)	17-05-2019
Jquery/Js Ajax (diff)	20-05-2019
JDBC/GC/Arrays	20-05-2019
Web Application Configuration	20-05-2019
Abstract Document – reviewed	21-05-2019
Demo – Project Review(3rd )	21-05-2019
Naming Convention/ Coding Standards	21-05-2019
Defined exception / joins/sub query	21-05-2019
UI – Validation/ alignments/css	21-05-2019
Final Project Review
Demo to client
Share Source code / DB script (Git Repository)